## Sheet1
CHECKLIST |  |  |  | CMS - Badminton
Project Start | 2018-12-11 |  |  |  |  | Project End | 2018-12-24
TASK | OWNER | PRIORITY | START | END | % COMPLETE | DONE | NOTES
Requirements | [5 empty] | 0
Introduction | Nguyễn Văn Quay | MEDIUM | 2018-12-18 | 2018-12-20 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Overall Description | Bùi Thanh Tân | MEDIUM | 2018-12-20 | 2018-12-22 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
External Interface Requirements | Trần Quang Linh | MEDIUM | 2018-12-20 | 2018-12-22 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
System Features | Dương Minh Trí | MEDIUM | 2018-12-16 | 2018-12-18 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Other nonfunctional requirements and other requirements | Nguyễn Thành Tín | MEDIUM | 2018-12-15 | 2018-12-16 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Design | [5 empty] | 0
Login and registration | Nguyễn Thành Tín | LOW | 2018-12-17 | 2018-12-20 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
Main screen | Nguyễn Thành Tín | HIGH | 2018-12-17 | 2018-12-20 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
Detail screen | Nguyễn Thành Tín | HIGH | 2018-12-17 | 2018-12-20 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
UML Diagram | Nguyễn Văn Quay | HIGH | 2018-12-16 | 2018-12-19 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
UML Diagram | Dương Minh Trí | HIGH | 2018-12-16 | 2018-12-19 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
| Trần Quang Linh | HIGH | 2018-12-16 | 2018-12-19 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
| Bùi Thanh Tân | HIGH | 2018-12-16 | 2018-12-19 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
Code - Front end | [5 empty] | 0
Registration | Nguyễn Thành Tín | MEDIUM | 2018-12-18 | 2018-12-20 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
Home screen | Trần Quang Linh | HIGH | 2018-12-18 | 2018-12-20 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
Detail screen | Trần Quang Linh | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Nguyễn Văn Quay | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Dương Minh Trí | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Bùi Thanh Tân | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
Code - Back end | [5 empty] | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Login and registration | Nguyễn Thành Tín | MEDIUM | 2018-12-21 | 2018-12-22 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Booking | Dương Minh Trí | MEDIUM | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Member | Nguyễn Văn Quay | MEDIUM | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
| Bùi Thanh Tân | MEDIUM | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
| Trần Quang Linh | MEDIUM | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Unit Testing | [5 empty] | 0
Re-check customer requirements | All team | HIGH | 2018-12-20 | 2018-12-23 | 100% | 0
Check requirements | All team | MEDIUM | 2018-12-20 | 2018-12-23 | 100% | 0
Check front end | All team | MEDIUM | 2018-12-20 | 2018-12-23 | 90% | 0
Check back end | All team | MEDIUM | 2018-12-20 | 2018-12-23 | 90% | 0